## Gantt Chart
GANTT CHART
PROJECT TITLE |  | TransitWise |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2023-09-05
Group Leader |  | Lucas Pfeifer
Group Members |  | Aidan Callan, David Lin, Uriel Cruz, Steven Macaluso, Jonathan Farnham
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2023 | W2 9/12/2023 |  | W3 9/19/2023 | W4 9/26/2023 | W5 10/3/2023 | W6 10/10/2023 | W7 10/17/2023 | W8 10/24/2023 | W9 10/31/2023 | W10 11/7/2023 | W11 11/14/2023 | W12 11/21/2023 | W13 11/28/2023 | W14 12/5/2023
1 | Project Conception and Initiation
1.1 | Setting up Github | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.1.1 | Setting up Webex Account | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.2 | Setting up XAMPP / Unreal Engine | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.3 | Assigning Group Leader | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.4 | Use Case Diagram | Aidan Callan | 2023-09-04 | 2023-09-11 | 7 | 100%
1.5 | Write description for all HTML Pages (see html_plan txt file in repo) | all | 2023-09-26 | 2023-10-10 | 14 | 85%
1.6 |  |  |  |  | 0
2 | Design |  |  |  | 0
2.1 | Basic Website template | David + Uriel | 2023-09-19 | 2023-09-26 | 7 | 100%
2.2 | log in pages | David + Uriel | 2023-09-19 | 2023-10-03 | 14 | 100%
2.3 | Homepage and flight info | David + Uriel | 2023-09-26 | 2023-10-03 | 7 | 85%
2.3.1 | User Account homepage and editing, front | David + Uriel | 2023-10-03 | 2023-10-17 | 14 | 100%
2.4 | Buttons for employees and admin | Uriel | 2023-10-31 | 2023-11-07 | 7 | 85%
2.5 | Finish user billing page | Uriel | 2023-10-31 | 2023-11-07 | 7 | 85%
2.6 | View ticket page | David | 2023-10-31 | 2023-11-07 | 7 | 85%
2.7 | Careers Page (needs backend) | Jonathan | 2023-10-31 | 2023-11-07 | 7 | 80%
2.8 | Time card page | Uriel | 2023-11-07 |  | -44587 | 90%
2.9 | View users info page (dropdown menu, could be used for both admin and employee) | Uriel | 2023-11-07 |  | -44587 | 85%
2.9.5 | User info separate pages | Uriel | 2023-11-28 |  | -44608 | 100%
2.1 | Destination page, deals page (could be combined) - ditched | David | 2023-11-07 |  | -44587 | 10%
2.11 |  |  |  |  | 0
3 | Parts and Assembly |  |  |  | 0
3.1 | User Data Tables | Lucas Pfeifer + Aidan | 2023-09-19 | 2023-09-19 | 0 | 100%
3.2 | Flight Data Collection/Input | Lucas | 2023-09-19 | 2023-09-26 | 7 | 100%
3.2.1 | Financial Transaction Simulator | Steven+Jonathan | 2023-09-19 | 2023-10-03 | 14 | 95%
3.2.2 | Employee/Users Data tables | Lucas + Aidan | 2023-09-19 | 2023-10-03 | 14 | 95%
3.3 | Ticket Data tables | Aidan | 2023-09-26 | 2023-10-03 | 7 | 100%
3.5 | Administrative data tables | Lucas + Aidan | 2023-10-03 | 2023-10-17 | 14 | 100%
3.6 | FAQ | David + Uriel | 2023-10-03 | 2023-10-17 | 14 | 100%
3.7 | Account Editing | David + Uriel | 2023-10-03 | 2023-10-24 | 21 | 100%
3.7.5 | Backend connection for above | Aidan | 2023-10-17 | 2023-10-24 | 7 | 95%
4.5 | Z report (includes backend) | Jonathan + Steven | 2023-10-03 | 2023-10-24 | 21 | 50%
5.5 | Refund ticket | Jonathan + Steven | 2023-10-03 | 2023-10-24 | 21 | 50%
6.5 | Checkout front and back | Jonathan + Steven | 2023-10-17 | 2023-10-31 | 14 | 90%
7.5 | Backend for admin portal (employee editing) | Lucas | 2023-10-17 | 2023-10-24 | 7 | 85%
7.5.5 | Backend for timecard | Aidan | 2023-11-28 |  |  | 45%
7.6 | Employee/Admin Login Backend | Lucas | 2023-10-31 | 2023-11-07 | 7 | 100%
8.5 | PHP User Class | Aidan | 2023-11-07 |  |  | 100%
9.5 | PHP Links class - ditched | Lucas | 2023-11-07 |  |  | 0%
9.6 | Important: view reservations and tickets | Lucas | 2023-11-07 | 2023-12-09 |  | 75%
9.7 | Customization with seating, class, baggage | Lucas | 2023-11-28 |  |  | 65%
9.8 | Feedback (frontend) | Jonathan |  | 2023-12-09 |  | 0%
9.8.5 | Feedback backend | Aidan |  | 2023-12-09 |  | 50%
9.9 | Important: Fix data tables (auto-increment and index) | Lucas | 2023-12-05 | 2023-12-09