## Gantt Chart
GANTT CHART
PROJECT TITLE |  | TransitWise |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2023-09-05
Group Leader |  | Lucas Pfeifer
Group Members |  | Aidan Callan, David Lin, Uriel Cruz, Steven Macaluso, Jonathan Farnham
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2023 | W2 9/12/2023 |  | W3 9/19/2023 | W4 9/26/2023 | W5 10/3/2023 | W6 10/10/2023 | W7 10/17/2023 | W8 10/24/2023 | W9 10/31/2023 | W10 11/7/2023 | W11 11/14/2023 | W12 11/21/2023 | W13 11/28/2023 | W14 12/5/2023
1 | Project Conception and Initiation
1.1 | Setting up Github | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.1.1 | Setting up Webex Account | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.2 | Setting up XAMPP / Unreal Engine | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.3 | Assigning Group Leader | all | 2023-09-04 | 2023-09-11 | 7 | 100%
1.4 | Use Case Diagram | Aidan Callan | 2023-09-04 | 2023-09-11 | 7 | 100%
1.5 | Learn Javascript for sql | all | 2023-09-18 |  | -44538
1.6 |  |  |  |  | 0
2 | Design |  |  |  | 0
2.1 | Basic Website template | David + Uriel | 2023-09-19 | 2023-09-26 | 7
2.2 | User acount and log in pages | David + Uriel | 2023-09-19 | 2023-10-03 | 14
2.3 |  |  |  |  | 0
2.3.1 |  |  |  |  | 0
2.4 |  |  |  |  | 0
2.5 |  |  |  |  | 0
2.6 |  |  |  |  | 0
2.7 |  |  |  |  | 0
2.8 |  |  |  |  | 0
2.9 |  |  |  |  | 0
2.1 |  |  |  |  | 0
2.11 |  |  |  |  | 0
3 | Parts and Assembly |  |  |  | 0
3.1 | User Data Tables | Lucas Pfeifer + Aidan | 2023-09-19 | 2023-09-19 | 0 | 100%
3.2 | Flight Data Collection/Input | Jonathan + Steven | 2023-09-19 | 2023-09-26 | 7
3.2.1 | Finacial Transaction Simulator | Steven+Jonathan | 2023-09-19 | 2023-10-03 | 14
3.2.2 | Employee Users | Lucas + Aidan | 2023-09-19 | 2023-10-03 | 14
3.3 |  |  |  |  | 0
3.3.1 |  |  |  |  | 0